## Slide 1: Project Tracker May 2017
By: Nasim

## Slide 2
Login Page creation | 19/05 | 19/05
Home page creation | 19/05 | 19/05
Database creation (Code first approach) | 20/05 | 20/05
Regression Test | 06/06 | 
Service desk | TBD | 
Bug fixing and support | TBD | 
Learning application
Weekly Status – May 22, 2017
Executive Summary
Prototype of Application architecture and DevOps practices for build , packaging and deployment pipelines for Dev, QA, UAT, PRD environment. Modules included are Database Project, Login, Dictionaries, Self Assessment test for foreign language learning.
Deliverables
Deliverables | Define | Build | Release | Rollout
Application architecture | 19/05/17 | 19/05/17 | 19/05/17 | 100%
Database Project with unit tests coverage | 20/05/17 | 20/05/17 | 20/05/17 | 50%
Application design with unit tests coverage | 20/05/17 | 21/05/17 | 21/05/17 | 20%
CI Build | 22/05/17 | 22/05/17 | 22/05/17 | 30%
Build
Overall
Risk | Get-To-Green Plan (GtG) | Owner | Due Date
Deployment environment is missing. | Needs deployment environment to check CI, CD pipelines | PritiX | 22/05/2017
R
A
G
Behind plan
Plan under pressure
On or ahead of plan
C
Complete
KEY
Milestones / Key Dates
Risks
Fourth week May’17
First week Jun’17
Fourth Quarter 2017
W3
Jan 25
Jan 25
Jan 25
Third week May’17
Assessment forms creation | 23/05 | 
Unit test coverage | 23/05 | 
Build and Release pipelines | 24/05 | 
Self assessment test for users and Dictionary creation.
Unit test coverage for Website and Database both.
Build , Release and Deployment pipelines for DEV, QA, UAT, PROD.
Functional Regression test suites (Coded UI)
Feedback and Support system(JIRA/BMC)
Upcoming Activities
W4
W1
W2
Planned Date
Actual / Forecast Date
Database project for automatic deployment of database related changes. Code first approach with Unit test coverage for DB As well.
Application using responsive UI by implementing Bootstrap.
Quality gates implementation by Unit test and Functional test coverage.
Bridge the Gap between DEV to PROD by implementing DevOps.
Highlights
Notes: Deliverables:
Dates in each phase – Actual or Forecast
Color fill – Status/Risk with respect to forecast date
Thick Borders – In Progress items.
Build Status:
Planned – Original planned scope/dates/budget
Amended/Forecast
Actual – Current
Actual % - Actual / planned
Color fill -- Status/Risk with respect to Amended/Forecast
Milestones
Color fill – Status/Risk with respect to forecast date
Thick Borders – In Progress items.
Top Risks
Color fill in Due date - Status/Risk with respect to due date

## Slide 3
DevOps Workflow
Notes: Deliverables:
Dates in each phase – Actual or Forecast
Color fill – Status/Risk with respect to forecast date
Thick Borders – In Progress items.
Build Status:
Planned – Original planned scope/dates/budget
Amended/Forecast
Actual – Current
Actual % - Actual / planned
Color fill -- Status/Risk with respect to Amended/Forecast
Milestones
Color fill – Status/Risk with respect to forecast date
Thick Borders – In Progress items.
Top Risks
Color fill in Due date - Status/Risk with respect to due date

## Slide 4
PritiX |  | मई-17 |  |  |  |  |  |  |  |  |  | जून-17 |  |  |  |  |  |  |  |  | 
 |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  | 
1 | Application workflow |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Design Application Architechure diagram |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | Database Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4 | Create database Project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5 | Create unit test for database |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6 | Application Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7 | Create web form application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
8 | Unit test project for application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
9 | Login module |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
10 | Dictionary module |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
11 | Assessment module |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
12 | Deployment Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
13 | CI Build setup |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
14 | CD build setup |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
15 | Release setup |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
16 | Deployment pipelines QA, UAT, PROD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
12 | Feedback/Support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
13 | Monitoring application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
14 | Implementation support system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Completed
 | Inprogress
 | Monitoring and improvement
 | Projected
Roadmap
Notes: Deliverables:
Dates in each phase – Actual or Forecast
Color fill – Status/Risk with respect to forecast date
Thick Borders – In Progress items.
Build Status:
Planned – Original planned scope/dates/budget
Amended/Forecast
Actual – Current
Actual % - Actual / planned
Color fill -- Status/Risk with respect to Amended/Forecast
Milestones
Color fill – Status/Risk with respect to forecast date
Thick Borders – In Progress items.
Top Risks
Color fill in Due date - Status/Risk with respect to due date

## Slide 5
Thank you!
Notes: Deliverables:
Dates in each phase – Actual or Forecast
Color fill – Status/Risk with respect to forecast date
Thick Borders – In Progress items.
Build Status:
Planned – Original planned scope/dates/budget
Amended/Forecast
Actual – Current
Actual % - Actual / planned
Color fill -- Status/Risk with respect to Amended/Forecast
Milestones
Color fill – Status/Risk with respect to forecast date
Thick Borders – In Progress items.
Top Risks
Color fill in Due date - Status/Risk with respect to due date